## Open items
PROJECT PHOENIX — CLUB 641
Opening date: 10/24 Tracker updated: 9/15
Item | Area | Owner | Due | Status | Cost code
Freezer door seal replacement | Refrigeration | Facilities | 9/11 | In progress | 4100
Deli case lighting | Deli | Facilities | 9/30 | Not started | 4200
Optical counter outlets | Optical | Electrical contractor | 10/3 | Not started | 4200
Card readers, 4 lanes | Front end | IT | 10/10 | Not started | 4300
Bakery oven vent inspection | Bakery | Facilities | 9/12 | Waiting | 4100
Parking lot striping | Exterior | Site contractor | 10/6 | In progress | 4400
Gas station lights | Gas |  | 10/17 | Not started
Shelving delivery | Sales floor | Merchandising | 9/22 | On order | 4300
Front door sensors | Front end | Facilities | 10/12 | Not started
Fire panel test | Safety | Facilities | 9/12 | Complete | 4500
Exterior signage | Exterior | Site contractor | 9/20 | Complete | 4400
Cart corral installation | Exterior | Site contractor | 10/14 | Not started
Illustrative data created for AI Connect training. Not a BJ's record.