## Slide 1
Project Phoenix — Week of 9/8
Club 641 · Opening 10/24
ON TRACK (4)
Exterior signage — Site contractor — 9/20
Shelving delivery — Merchandising — 9/22
Parking lot striping — Site contractor — 10/6
Card readers, 4 lanes — IT — 10/10
AT RISK (2)
Fire panel test — Facilities — 9/12 (was 9/5)
Optical counter outlets — Electrical contractor — 10/3
NEEDS A DECISION (1)
Gas station lights — Owner not assigned — 10/17
Ask of this group: Name an owner for the gas station lights by Friday.
Illustrative material created for AI Connect training. Not a BJ's record.